## Sprint data
Sprint | Planned | Done | Reliability % | Median lead | P85 lead | Bugs opened | Bugs closed | Open at end | Sev1 | Sev2 | Incidents | Avg velocity
S1 | 30 | 24 | 80 | 9.5 | 15 | 7 | 4 | 15 | 1 | 1 | 2 | 31.1
S2 | 32 | 29 | 91 | 8.8 | 14 | 9 | 8 | 16 | 0 | 1 | 1 | 31.1
S3 | 34 | 31 | 91 | 8 | 13 | 6 | 7 | 15 | 0 | 0 | 0 | 31.1
S4 | 34 | 33 | 97 | 7.5 | 12 | 8 | 8 | 15 | 0 | 1 | 1 | 31.1
S5 | 28 | 26 | 93 | 8.2 | 14 | 5 | 6 | 14 | 0 | 0 | 0 | 31.1
S6 | 36 | 34 | 94 | 6.9 | 11 | 4 | 6 | 12 | 0 | 0 | 0 | 31.1
S7 | 36 | 35 | 97 | 6.4 | 10 | 5 | 5 | 12 | 0 | 0 | 0 | 31.1
S8 | 38 | 37 | 97 | 6 | 9.5 | 3 | 5 | 10 | 0 | 0 | 0 | 31.1
Total | 268 | 249 | 92.9 |  |  | 47 | 49 |  | 1 | 3 | 4

## Sprint 8 burndown
Working day | Ideal | Actual
0 | 38 | 38
1 | 34.2 | 38
2 | 30.4 | 34
3 | 26.6 | 31
4 | 22.8 | 27
5 | 19 | 24
6 | 15.2 | 20
7 | 11.4 | 15
8 | 7.6 | 11
9 | 3.8 | 6
10 | 0 | 1

## KPI
Indicador | Valor | Detalhe
Average velocity | 31,1 pts | Last 3 sprints: 35.3
Commitment reliability | 92.9% | 249 of 268 points
Median lead time (S8) | 6,0 d | Decrease 37% since S1
Open bugs | 10 | high point of 16 at S2
Incidents in 8 releases | 4 | 3 releases afected, 0 on last 4
Debt hours closed | 272 / 860 h | 6 of 13 itens (31,6%)

## Debts closed
Item | Descrição | Horas
EX-01 | Secrets vault | 16
EX-02 | Logging CVE patch | 8
EX-03 | TLS fix | 32
EX-04 | Premium tests | 80
EX-06 | Resilience, payment gateway | 56
EX-08 | Tracing | 80
Total |  | 272